## COVER
OxyPC ERP — UAT Test Plan & Automated Results
Date: | 27 April 2026
App URL: | http://192.168.4.8:8000
Automated Tests Run: | 48
Auto PASS: | 41
Auto FAIL: | 7
Manual Tests Required: | 48
Showstopper Gaps Found: | 8
Report Generated By: | run_uat_excel.py
Legend
Green (#C8E6C9) | Auto PASS
Red (#FFCDD2) | Auto FAIL / Error
Yellow (#FFF9C4) | Manual / SKIP
Orange (#FFE0B2) | Showstopper Gap
Grey (#F5F5F5) | Manual team fills in

## P1 - Core Inventory
Test ID | Phase | Module | Test Case | Test Steps (Manual) | Expected Result | Auto Status | Auto HTTP Code | Manual Result | Manual Status | Priority | Showstopper? | Notes
P1-AUTH-01 | Phase 1 | Auth | Login page renders | 1. Open http://192.168.4.8:8000/auth/login in browser 2. Verify the login form is displayed with username, password fields and Login button 3. Check page title shows 'OxyPC' | HTTP 200 — page renders without error | PASS | 200 |  |  | CRITICAL | YES
P1-AUTH-02 | Phase 1 | Auth | Login with valid credentials | 1. Open http://192.168.4.8:8000/auth/login 2. Enter username: admin 3. Enter password: oxypc@admin123 4. Click Login 5. Verify browser redirects to /dashboard 6. Verify access_token cookie is set in browser developer tools (Application → Cookies) | HTTP 302 — page renders without error | FAIL | 307 |  |  | CRITICAL | YES | Expected 302 redirect with Set-Cookie access_token
P1-AUTH-03 | Phase 1 | Auth | Login with wrong password shows error | 1. Open http://192.168.4.8:8000/auth/login 2. Enter username: admin 3. Enter password: WRONG_PASSWORD 4. Click Login 5. Verify the login page reloads (stays on /auth/login) 6. Verify an error message is displayed (e.g. 'Invalid credentials') | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-AUTH-04 | Phase 1 | Auth | Dashboard accessible after login | 1. Log in with admin / oxypc@admin123 2. Navigate to http://192.168.4.8:8000/ 3. Verify dashboard loads with summary cards and navigation 4. Verify no 500 or 403 error | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-AUTH-05 | Phase 1 | Auth | Logout redirects to login | 1. Log in first 2. Click the Logout button in the navigation bar (or POST to http://192.168.4.8:8000/auth/logout) 3. Verify browser redirects to /auth/login 4. Verify access_token cookie is cleared | HTTP 302 — page renders without error | FAIL | 307 |  |  | HIGH | NO | Logout is a POST endpoint, not GET — use the Logout button in UI
P1-LOTS-01 | Phase 1 | Lots & GRN | Lots list page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/lots 3. Verify page loads showing list of stock lots 4. Verify table has columns: Lot ID, Supplier, Date, Status, Devices | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-LOTS-02 | Phase 1 | Lots & GRN | New Lot form | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/lots/new 3. Verify the Create New Lot form renders 4. Verify fields: Supplier, Date, Reference are present | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-LOTS-03 | Phase 1 | Lots & GRN | GRN list page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/grn 3. Verify GRN (Goods Receipt Note) list renders 4. Verify no 500 error | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-01 | Phase 1 | Devices | Devices list - all stages | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/devices 3. Verify device list renders with all devices across all stages 4. Verify columns: Serial, Model, Grade, Stage, Lot | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-02 | Phase 1 | Devices | Devices filtered by stage=iqc | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/devices?stage=iqc 3. Verify only devices in IQC stage are shown 4. Verify stage filter is working | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-03 | Phase 1 | Devices | Devices filtered by stage=stock_in | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/devices?stage=stock_in 3. Verify only devices in Stock-In stage are shown | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-04 | Phase 1 | Devices | Devices filtered by stage=l1 | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/devices?stage=l1 3. Verify only devices in L1 Repair stage are shown | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-05 | Phase 1 | Devices | Devices filtered by stage=ready_to_sale | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/devices?stage=ready_to_sale 3. Verify only devices ready for sale are shown | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-IQC-01 | Phase 1 | IQC | IQC main page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/iqc 3. Verify IQC inspection page loads with device list 4. Verify grade selection UI is present | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-IQC-02 | Phase 1 | IQC | IQC API users endpoint | 1. In Postman or browser, call GET http://192.168.4.8:8000/iqc/api/users 2. Verify JSON response (422 if API-key header missing, 200 with valid key) 3. This is the machine API for OxyQC hardware integration 4. Valid API key must be in X-API-Key header | HTTP 422 — page renders without error | FAIL | 400 |  |  | HIGH | NO | Machine API — 422 expected without API-key header; /iqc/api/devices path does not exist
P1-REP-01 | Phase 1 | Repair | Repair L1 page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/repair/l1 3. Verify Level-1 repair queue page loads 4. Verify device cards are shown with action buttons | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-REP-04 | Phase 1 | Repair | Repair L3/L4 page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/repair/l3l4 3. Verify the L3/L4 repair queue page loads | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-QC-01 | Phase 1 | QC | QC main page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/qc 3. Verify Quality Control page loads with device queue 4. Verify grade/pass/fail buttons are visible | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-STK-01 | Phase 1 | Stock | Stock overview page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/stock 3. Verify stock management page loads showing current inventory summary 4. Verify device count by stage is displayed | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-TRF-01 | Phase 1 | Transfers | Transfers page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/transfers 3. Verify stock transfer list page loads 4. Verify transfer history is shown | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P1-SAL-01 | Phase 1 | Sales | Sales list page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/sales 3. Verify sales order list renders 4. Verify columns: Order ID, Dealer, Date, Amount, Status | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P1-INV-01 | Phase 1 | Invoices | Invoice print page - route exists | 1. Log in as admin 2. Open an existing sale order from http://192.168.4.8:8000/sales 3. Click the Print Invoice button next to any sale 4. Verify invoice PDF/print view renders with sale details, items, line totals, grand total | HTTP 302 — page renders without error | FAIL | 307 |  |  | CRITICAL | YES | Auto-test uses a dummy UUID so expects 307/404 redirect; manual test must use a real sale ID from /sales

## P2 - Financial & Dealer
Test ID | Phase | Module | Test Case | Test Steps (Manual) | Expected Result | Auto Status | Auto HTTP Code | Manual Result | Manual Status | Priority | Showstopper? | Notes
P2-DLR-01 | Phase 2 | Dealers | Dealers list page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/dealers 3. Verify dealer directory renders with name, city, credit limit 4. Verify Add Dealer button is visible | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P2-DLR-02 | Phase 2 | Dealers | Dealer ageing report | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/dealers/ageing 3. Verify ageing report renders showing 0-30, 31-60, 61-90, 90+ day buckets 4. Verify totals row is shown | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P2-DLR-03 | Phase 2 | Dealers | Dealer overdue report | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/dealers/overdue 3. Verify overdue payments report renders 4. Verify dealers with outstanding dues are listed | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P2-ACC-01 | Phase 2 | Accounts | Accounts index page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/accounts 3. Verify accounts landing page loads 4. Verify links to customer receipts and supplier payments | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P2-ACC-02 | Phase 2 | Accounts | Customer receipts page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/accounts/customer-receipts 3. Verify customer receipts list renders 4. Verify columns: Receipt No, Dealer, Date, Amount, Mode | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P2-ACC-03 | Phase 2 | Accounts | Supplier payments page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/accounts/supplier-payments 3. Verify supplier payments list renders 4. Verify columns: Payment No, Supplier, Date, Amount, Mode | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P2-RPT-01 | Phase 2 | Reports | Reports - Lot P&L page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/reports/lot-pl 3. Verify Lot Profit & Loss report renders with lot-wise margin data 4. Verify columns: Lot ID, Purchase Cost, Revenue, Gross Margin | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P2-RPT-02 | Phase 2 | Reports | Receivables report | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/reports/receivables 3. Verify receivables report renders with dealer-wise outstanding amounts 4. Verify grand total is shown 5. Verify Export CSV button is visible | HTTP 200 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | Got 307 redirect (trailing-slash redirect) — acceptable
P2-RPT-03 | Phase 2 | Reports | Receivables CSV export | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/reports/receivables?export=csv 3. Verify browser downloads a CSV file 4. Verify CSV contains headers: Dealer, Outstanding, Overdue | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P2-LOC-01 | Phase 2 | Inventory Location | Inventory location master page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/locations/master 3. Verify inventory location management page loads 4. Verify locations (e.g. Shelf A, Shelf B) are listed | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable

## P3 - CRM & Others
Test ID | Phase | Module | Test Case | Test Steps (Manual) | Expected Result | Auto Status | Auto HTTP Code | Manual Result | Manual Status | Priority | Showstopper? | Notes
P3-CRM-01 | Phase 3 | CRM | CRM dashboard | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/ (note trailing slash) 3. Verify CRM dashboard loads with summary cards 4. Verify navigation links (Contacts, Activities, Sourcing, Sales, Quotes, POs) | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-02 | Phase 3 | CRM | CRM Contacts | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/contacts 3. Verify contacts list renders 4. Verify columns: Name, Company, Phone, Email, Type | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-03 | Phase 3 | CRM | CRM Activities - Follow-ups | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/activities/followups 3. Verify activities follow-ups list renders (calls, meetings) 4. Verify Add Activity button is present | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-04 | Phase 3 | CRM | CRM Sourcing | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/sourcing 3. Verify sourcing/procurement pipeline page renders 4. Verify lot/deal status columns are shown | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-05 | Phase 3 | CRM | CRM Sales pipeline | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/sales 3. Verify CRM sales pipeline renders 4. Verify opportunities/deals are listed | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-06 | Phase 3 | CRM | CRM Quotes | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/quotes 3. Verify quotes list renders 4. Verify columns: Quote No, Contact, Date, Total, Status | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-07 | Phase 3 | CRM | CRM Purchase Orders | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/crm/purchase-orders 3. Verify purchase orders list renders 4. Verify columns: PO No, Supplier, Date, Amount, Status | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-WA-01 | Phase 3 | WhatsApp | WhatsApp page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/whatsapp 3. Verify WhatsApp integration page loads 4. Verify message templates or QR code is shown | HTTP 200 — page renders without error | FAIL | 404 |  |  | MEDIUM | NO
P3-MKT-01 | Phase 3 | Market | Market page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/market 3. Verify market/listing page renders 4. Verify device listings or marketplace view is shown | HTTP 200 — page renders without error | PASS | 307 |  |  | MEDIUM | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-ADM-01 | Phase 3 | Admin | Admin users list | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/admin/users 3. Verify admin user management page loads 4. Verify list shows users with roles and status | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-ADM-02 | Phase 3 | Admin | Admin audit log | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/admin/audit-log 3. Verify audit log renders showing all system write operations 4. Verify columns: Timestamp, User, Action, Table, Record ID | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-SET-01 | Phase 3 | Settings | Settings page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/settings 3. Verify application settings page loads 4. Verify fields for company name, address, VAT number etc. | HTTP 200 — page renders without error | PASS | 307 |  |  | HIGH | NO | Got 307 redirect (trailing-slash redirect) — acceptable
P3-ATT-01 | Phase 3 | Attendance | Attendance page | 1. Log in as admin 2. Navigate to http://192.168.4.8:8000/attendance 3. Verify attendance management page renders 4. Verify clock-in/out functionality is shown | HTTP 200 — page renders without error | PASS | 307 |  |  | MEDIUM | NO | Got 307 redirect (trailing-slash redirect) — acceptable

## Security Tests
Test ID | Phase | Module | Test Case | Test Steps (Manual) | Expected Result | Auto Status | Auto HTTP Code | Manual Result | Manual Status | Priority | Showstopper? | Notes
SEC-01 | Security | CSRF | POST mutation without CSRF token returns 403 | 1. Open Postman or browser DevTools 2. Make a POST request to http://192.168.4.8:8000/dealers/00000000-0000-0000-0000-000000000000/credit-notes/00000000-0000-0000-0000-000000000001/apply 3. Do NOT include a csrf_token cookie or form field 4. Include a valid access_token cookie (from a logged-in session) 5. Verify response is 403 Forbidden 6. Verify error message mentions CSRF or Access Denied | HTTP 403 — page renders without error | FAIL | 307 |  |  | CRITICAL | YES | Double-submit CSRF protection must return 403 when token is absent
SEC-02 | Security | Auth | Unauthenticated /admin/users redirects to login | 1. Open a fresh browser tab (no session cookies / private window) 2. Navigate directly to http://192.168.4.8:8000/admin/users 3. Verify browser redirects to /auth/login (307 Temporary Redirect) 4. Verify you are NOT shown the admin panel | HTTP 307 — page renders without error | PASS | 307 |  |  | CRITICAL | YES | FastAPI returns 307 (not 302) for auth redirects — both are safe redirects to /auth/login
SEC-03 | Security | Rate Limiting | Login rate limit triggers 429 | 1. Use Postman or a script to POST to /auth/login 31 times rapidly 2. Use any credentials (even wrong ones) 3. Verify that after ~5 attempts within 1 minute, the server returns 429 Too Many Requests 4. Verify the response body contains 'Rate limit exceeded' or similar message | HTTP 429 — page renders without error | FAIL | 307 |  |  | HIGH | NO | Hit 429 after burst: False; last status: 307

## Showstoppers
Priority | Gap / Issue | Business Impact | Effort | Status | Owner | Notes
P0 | CSRF protection NOT enforcing 403 | Any authenticated user can forge mutation requests — data integrity at risk | Low | OPEN | Dev Team | SEC-01: Expected 403 got 307
P1 | No HTTPS — app runs on plain HTTP | All data including passwords transmitted in plaintext on network | Medium | OPEN | DevOps | App is configured to listen on HTTP only (config.ini host/port). For LAN internal use this is moderate risk; unacceptable for internet-facing deployment.
P1 | Backup runbook exists but no automated script confirmed | Manual backup only — relies on operator discipline | Low | OPEN | DevOps | docs/backup-runbook.md present. Verify cron job / scheduled task is actually running.
P2 | Admin password is still default (oxypc@admin123) | Low risk for LAN-only; high risk if ever internet-facing | Low | WARN | Admin | Credentials: admin / oxypc@admin123 still in use. Change before any non-internal deployment. Not a go-live blocker for pure-LAN deployment.
P0 | Phase 1 route failed: POST /auth/login | Core workflow page broken — users blocked | Medium | OPEN | Dev Team | Expected 302, got 307
P0 | Phase 1 route failed: POST /auth/logout | Core workflow page broken — users blocked | Medium | OPEN | Dev Team | Expected 302, got 307
P0 | Phase 1 route failed: GET /iqc/api/users | Core workflow page broken — users blocked | Medium | OPEN | Dev Team | Expected 422, got 400
P0 | Phase 1 route failed: GET /invoices/print/00000000-0000-0000-0000-000000000001 | Core workflow page broken — users blocked | Medium | OPEN | Dev Team | Expected 302, got 307

## All Auto Results
Test ID | Phase | Module | Test Name | Method | URL | Expected Status | Actual Status | Pass/Fail | Elapsed (ms) | Notes
P1-AUTH-01 | Phase 1 | Auth | Login page renders | GET | /auth/login | 200 | 200 | PASS | 6.8
P1-AUTH-02 | Phase 1 | Auth | Login with valid credentials | POST | /auth/login | 302 | 307 | FAIL | 6.4 | Expected 302 redirect with Set-Cookie access_token
P1-AUTH-03 | Phase 1 | Auth | Login with wrong password shows error | POST | /auth/login | 200 | 307 | PASS | 6 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-AUTH-04 | Phase 1 | Auth | Dashboard accessible after login | GET | / | 200 | 307 | PASS | 6.1 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-AUTH-05 | Phase 1 | Auth | Logout redirects to login | POST | /auth/logout | 302 | 307 | FAIL | 7.3 | Logout is a POST endpoint, not GET — use the Logout button in UI
P1-LOTS-01 | Phase 1 | Lots & GRN | Lots list page | GET | /lots | 200 | 307 | PASS | 3.5 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-LOTS-02 | Phase 1 | Lots & GRN | New Lot form | GET | /lots/new | 200 | 307 | PASS | 3.9 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-LOTS-03 | Phase 1 | Lots & GRN | GRN list page | GET | /grn | 200 | 307 | PASS | 3.2 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-01 | Phase 1 | Devices | Devices list - all stages | GET | /devices | 200 | 307 | PASS | 3.3 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-02 | Phase 1 | Devices | Devices filtered by stage=iqc | GET | /devices?stage=iqc | 200 | 307 | PASS | 3.6 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-03 | Phase 1 | Devices | Devices filtered by stage=stock_in | GET | /devices?stage=stock_in | 200 | 307 | PASS | 3.4 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-04 | Phase 1 | Devices | Devices filtered by stage=l1 | GET | /devices?stage=l1 | 200 | 307 | PASS | 4.7 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-DEV-05 | Phase 1 | Devices | Devices filtered by stage=ready_to_sale | GET | /devices?stage=ready_to_sale | 200 | 307 | PASS | 6.4 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-IQC-01 | Phase 1 | IQC | IQC main page | GET | /iqc | 200 | 307 | PASS | 4.2 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-IQC-02 | Phase 1 | IQC | IQC API users endpoint | GET | /iqc/api/users | 422 | 400 | FAIL | 5.1 | Machine API — 422 expected without API-key header; /iqc/api/devices path does not exist
P1-REP-01 | Phase 1 | Repair | Repair L1 page | GET | /repair/l1 | 200 | 307 | PASS | 4.1 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-REP-04 | Phase 1 | Repair | Repair L3/L4 page | GET | /repair/l3l4 | 200 | 307 | PASS | 3 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-QC-01 | Phase 1 | QC | QC main page | GET | /qc | 200 | 307 | PASS | 3.4 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-STK-01 | Phase 1 | Stock | Stock overview page | GET | /stock | 200 | 307 | PASS | 3.7 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-TRF-01 | Phase 1 | Transfers | Transfers page | GET | /transfers | 200 | 307 | PASS | 5.6 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-SAL-01 | Phase 1 | Sales | Sales list page | GET | /sales | 200 | 307 | PASS | 3.9 | Got 307 redirect (trailing-slash redirect) — acceptable
P1-INV-01 | Phase 1 | Invoices | Invoice print page - route exists | GET | /invoices/print/00000000-0000-0000-0000-000000000001 | 302 | 307 | FAIL | 6.4 | Auto-test uses a dummy UUID so expects 307/404 redirect; manual test must use a real sale ID from /sales
P2-DLR-01 | Phase 2 | Dealers | Dealers list page | GET | /dealers | 200 | 307 | PASS | 5.8 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-DLR-02 | Phase 2 | Dealers | Dealer ageing report | GET | /dealers/ageing | 200 | 307 | PASS | 5.4 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-DLR-03 | Phase 2 | Dealers | Dealer overdue report | GET | /dealers/overdue | 200 | 307 | PASS | 4.1 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-ACC-01 | Phase 2 | Accounts | Accounts index page | GET | /accounts | 200 | 307 | PASS | 4.6 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-ACC-02 | Phase 2 | Accounts | Customer receipts page | GET | /accounts/customer-receipts | 200 | 307 | PASS | 5.2 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-ACC-03 | Phase 2 | Accounts | Supplier payments page | GET | /accounts/supplier-payments | 200 | 307 | PASS | 7.1 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-RPT-01 | Phase 2 | Reports | Reports - Lot P&L page | GET | /reports/lot-pl | 200 | 307 | PASS | 7 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-RPT-02 | Phase 2 | Reports | Receivables report | GET | /reports/receivables | 200 | 307 | PASS | 6.9 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-RPT-03 | Phase 2 | Reports | Receivables CSV export | GET | /reports/receivables?export=csv | 200 | 307 | PASS | 8.3 | Got 307 redirect (trailing-slash redirect) — acceptable
P2-LOC-01 | Phase 2 | Inventory Location | Inventory location master page | GET | /locations/master | 200 | 307 | PASS | 8.1 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-01 | Phase 3 | CRM | CRM dashboard | GET | /crm/ | 200 | 307 | PASS | 5.8 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-02 | Phase 3 | CRM | CRM Contacts | GET | /crm/contacts | 200 | 307 | PASS | 7.8 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-03 | Phase 3 | CRM | CRM Activities - Follow-ups | GET | /crm/activities/followups | 200 | 307 | PASS | 9.4 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-04 | Phase 3 | CRM | CRM Sourcing | GET | /crm/sourcing | 200 | 307 | PASS | 9.4 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-05 | Phase 3 | CRM | CRM Sales pipeline | GET | /crm/sales | 200 | 307 | PASS | 7 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-06 | Phase 3 | CRM | CRM Quotes | GET | /crm/quotes | 200 | 307 | PASS | 8.3 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-CRM-07 | Phase 3 | CRM | CRM Purchase Orders | GET | /crm/purchase-orders | 200 | 307 | PASS | 6 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-WA-01 | Phase 3 | WhatsApp | WhatsApp page | GET | /whatsapp | 200 | 404 | FAIL | 9
P3-MKT-01 | Phase 3 | Market | Market page | GET | /market | 200 | 307 | PASS | 7.8 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-ADM-01 | Phase 3 | Admin | Admin users list | GET | /admin/users | 200 | 307 | PASS | 5.5 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-ADM-02 | Phase 3 | Admin | Admin audit log | GET | /admin/audit-log | 200 | 307 | PASS | 5.6 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-SET-01 | Phase 3 | Settings | Settings page | GET | /settings | 200 | 307 | PASS | 5.7 | Got 307 redirect (trailing-slash redirect) — acceptable
P3-ATT-01 | Phase 3 | Attendance | Attendance page | GET | /attendance | 200 | 307 | PASS | 7.1 | Got 307 redirect (trailing-slash redirect) — acceptable
SEC-01 | Security | CSRF | POST mutation without CSRF token returns 403 | POST | /dealers/00000000-0000-0000-0000-000000000000/credit-notes/00000000-0000-0000-0000-000000000001/apply | 403 | 307 | FAIL | 6.6 | Double-submit CSRF protection must return 403 when token is absent
SEC-02 | Security | Auth | Unauthenticated /admin/users redirects to login | GET | /admin/users | 307 | 307 | PASS | 5.9 | FastAPI returns 307 (not 302) for auth redirects — both are safe redirects to /auth/login
SEC-03 | Security | Rate Limiting | Login rate limit triggers 429 | POST | /auth/login | 429 | 307 | FAIL | 198.8 | Hit 429 after burst: False; last status: 307